## Potential Statutory Process Timeline
Date	Consultation / Meetings	Time	Venue
25th February 2019	Start of consultation by Governing Body and Local Authority. / Responses can be submitted for the next four weeks
	Publication of Statutory Notice of proposals
14th March 2019	Drop-in meeting with Parents/carers / Meet with school staff and governors / Drop-in meeting with local community and other interested parties	3.15 pm / 4:15 pm / 4.30 pm	All Saints Infant School
Sunday 24th March 2019	Last date for return of consultation Response Forms
25th March – 5th April 2019	Analysis of consultation outcomes by Governing Body and Local Authority for reports to County Council
Monday 20th May 2019	Decision by County Council elected Members on the consultation outcomes
Sunday 16th June 2019	Any appeal to the Schools Adjudicator on the statutory process for prescribed alterations must be made by this day.
September 2021	Depending on County Council decision, existing Infant School converts to Primary School status